## Client Engagement & Project Dev
Client Engagement & Project Development Process
| No. | 阶段 (Stage) | 详细内容 (Details)
| 1 | Requirement Assessment | * Client's project expectations (Function, materials, market, etc.)
|  | (需求评估) | * Client reference materials (Samples, concepts, sketches, or 2D/3D files)
* Project evaluation (Feasibility, reliability, and technical process selection)
* Risk assessment and cost calculation
| 2 | Agreement Signing | * NDA (Non-Disclosure Agreement)
|  | (协议签署) | * Responsibilities and tasks of all parties
| 3 | Engineering Design | * Establish printable and mold-ready 3D models based on client samples, sketches, or 2D/3D files, including appropriate rendering for preliminary evaluation.
(工程设计)
| 4 | Prototype Confirmation | * Sample size prototyping
|  | (原型确认) | * Client review for 3D modeling improvements or modifications
| 5 | Mold & Tooling | * Sample size molds
Client Engagement & Due Diligence |  |  |  | ORDER & MASS PRODUCTION
|  | (模具工装) | * Jigs and fixtures
| 6 | Initial Sample Validation | * Material preparation
|  | (初样验证) | * Sample manufacturing
* Client evaluation
| 7 | Full Scale Molds | * Standard grading based on client requirements
|  | (全套模具) | * Establish 3D files for mold opening
* Full range of size molds & accessory molds
| 8 | Full Size Confirmation | * Preparation of materials and packaging
|  | (全码确认) | * Sample manufacturing
* Client evaluation
| 9 | SOP Development | * Streamline the entire production process
|  | (SOP制作) | * Establish standard workflows & evaluate every stage
* Training and meetings: Familiarization with production specifications, manufacturing standards, and inspection standards